## Risk Matrix
RISK MATRIX |  |  | LIKELIHOOD
|  |  | Rare | Unlikely | Possible | Likely | Almost Certain
|  | (description) | the event is highly improbable, but still within the realm of possibility | while possible, the event is rare or may occur under special circumstances | the event could happen, but not often | the event has a high chance of happening | a situation where the event is expected to happen frequently
CONSEQUENCE | Severe | a situation where the impact is devastating, leading to major financial loss, reputational damage, and long-term operational disruption | HIGH | VERY HIGH | VERY HIGH | EXTREME | EXTREME
| Major | Indicate significant damage to operations and reputation, but with some possibility of recovery | HIGH | HIGH | VERY HIGH | VERY HIGH | EXTREME
| Moderate | the scenario where the impact is noticeable but manageable, with some downtime or financial loss | LOW | MEDIUM | MEDIUM | HIGH | VERY HIGH
| Minor | the event causes only slight disruptions | VERY LOW | LOW | MEDIUM | MEDIUM | HIGH
| Insignificant | minimal impact, such as a low-level breach where the consequences are negligible | VERY LOW | VERY LOW | LOW | MEDIUM | MEDIUM

## Risk Assessment
Context - Asset(s) that we are trying to protect
- Customer Data: Personally identifiable information (PII) stored on the company’s databases. - Intellectual Property (IP): Proprietary designs, algorithms, and business models. - Financial Information: Company’s transaction history, banking details, and employee payroll data.
Risk |  |  |  |  | Inherent Risk Rating |  |  | Current Risk Rating |  |  |  |  | Target Risk Rating
ID | Title | Description | Sources or Causes of Risk | Consequences of Risk | Likelihood | Consequence | Risk Level | Existing control measures | Effectiveness of exisitng control measures | Likelihood | Consequence | Risk Level | Additional control measures | Effectiveness of additional control measures | Likelihood | Consequence | Risk Level
R01 | Cyberattack on Database (Customer Data Breach) | This scenario involves a sophisticated cyberattack targeting the company’s customer database. The attackers may use tactics such as phishing, malware, or exploiting vulnerabilities in the company's systems to gain unauthorized access to sensitive customer information, including personally identifiable information (PII) like names, addresses, and payment details. | frequent attempts of phishing and malware campaigns | significant reputational damage and financial losses | Likely | Severe | EXTREME | firewalls, encryption, and multi-factor authentication | Excellent / Good / Moderate / Weak Good | Possible | Major | VERY HIGH | Accept / Treat / Avoid / Transfer Treat Implement regular security audits to identify vulnerabilities proactively. Upgrade intrusion detection systems (IDS) to detect suspicious behavior early. Conduct regular employee security awareness training to reduce risks from phishing and social engineering. Perform regular penetration testing to identify and resolve weaknesses. | Excellent / Good / Moderate / Weak Excellent | Unlikely | Moderate | MEDIUM
R02 | Insider Threat – IP Theft by a Disgruntled Employee | In this scenario, an employee with authorized access to the company's intellectual property (IP), such as proprietary designs, algorithms, or business strategies, steals this information either to sell it to competitors or to start a competing venture. | low-level employee dissatisfaction and access to sensitive data | loss of IP, damaging competitive advantage | Possible | Major | VERY HIGH | strict role-based access controls, data loss prevention systems, and regular audits | Excellent / Good / Moderate / Weak Moderate | Unlikely | Moderate | MEDIUM | Accept / Treat / Avoid / Transfer Treat Implement role-based access control (RBAC) to ensure that employees only access the data necessary for their role. Deploy data loss prevention (DLP) solutions to monitor and prevent unauthorized data transfer. Perform regular audits of employee activities, especially those in high-risk roles with access to sensitive information. Set up a whistleblower policy to encourage reporting of suspicious activity. | Excellent / Good / Moderate / Weak Good | Rare | Minor | VERY LOW
R03 | Natural Disaster – Data Center Damage | This scenario considers the impact of a natural disaster, such as a flood, earthquake, or fire, that could physically damage the client’s data center. | geographical location less prone to disasters | long-term outage of key systems and loss of availability | Rare | Major | HIGH | like disaster recovery plans, bcp and backup systems | Excellent / Good / Moderate / Weak Good | Rare | Moderate | LOW | Accept / Treat / Avoid / Transfer Treat Establish off-site backups in geographically diverse locations to avoid complete data loss. Invest in cloud infrastructure to enable faster recovery and maintain uptime. Implement redundant data centers for high availability and resilience against physical disasters. | Excellent / Good / Moderate / Weak Excellent | Rare | Minor | VERY LOW
R04 | student to provide a description | student to provide a description | student to provide a description | student to provide a description |  |  |  | student to provide a description | Excellent / Good / Moderate / Weak student to pick effectiveness and provide a description of exisitng contol measures |  |  |  | Accept / Treat / Avoid / Transfer student to pick mitigating action and provide a description of any additional contol measures | Excellent / Good / Moderate / Weak student to pick effectiveness and provide a description of any additional contol measures
R05 | student to provide a description | student to provide a description | student to provide a description | student to provide a description |  |  |  | student to provide a description | Excellent / Good / Moderate / Weak student to pick effectiveness and provide a description of exisitng contol measures |  |  |  | Accept / Treat / Avoid / Transfer student to pick mitigating action and provide a description of any additional contol measures | Excellent / Good / Moderate / Weak student to pick effectiveness and provide a description of any additional contol measures
Note on L6: Excellent Control - Highly effective and very fit for purpose. It substantially reduces the likelihood and/or consequence of the risk. It is cost effective. Good Control - Effective and fit for purpose. It reduces the likelihood and/or Consequence of the risk. It is relatively cost effective. Moderate Control - Moderately effective in reducing likelihood and/or consequence. May be able to be improved. May not be entirely cost effective. Weak Control - Does not exist, or is inadequate, ineffective or marginally effective in reducing likelihood and/or consequence. It is not cost effective
Note on R6: Excellent Control - Highly effective and very fit for purpose. It substantially reduces the likelihood and/or consequence of the risk. It is cost effective. Good Control - Effective and fit for purpose. It reduces the likelihood and/or Consequence of the risk. It is relatively cost effective. Moderate Control - Moderately effective in reducing likelihood and/or consequence. May be able to be improved. May not be entirely cost effective. Weak Control - Does not exist, or is inadequate, ineffective or marginally effective in reducing likelihood and/or consequence. It is not cost effective